## Sheet1
| 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | Owner | Date Completed
Assigned Project and Team | [15 empty] | All | 2022-01-24
Sponsor Introduction | [15 empty] | All | 2022-01-25
Brain Storm Stage | [9 empty] | Not started | [5 empty] | All | 2022-01-31
Distribution of Subsections | [9 empty] | In Progress | [5 empty] | All | 2022-01-28
Concept of Operations | [9 empty] | Completed | [5 empty] | All | 2022-02-19
Research | [9 empty] | Behind Schedule | [5 empty] | All | 2022-02-21
Research and Choose AC Unit | [15 empty] | All | 2022-02-21
Research Microcontroller Requirements | [15 empty] | Yarentzy | 2022-02-21
Choose Microcontroller | [15 empty] | Yarentzy | 2022-02-21
Download and begin testing with Android Studio | [15 empty] | Martin | 2022-02-21
Submit Preliminary Parts Request | [15 empty] | All | 2022-02-22
App layout and acquire cellular modem, sim, and antenna | [15 empty] | Martin | 2022-02-22
Functional System Requirements | [15 empty] | All | 2022-02-23
Interface Control Document | [15 empty] | All | 2022-02-23
Midterm Presentation | [15 empty] | All | 2022-02-23
Download MPLAB Software and Obtain Access to Debugger | [15 empty] | Yarentzy | 2022-02-21
Familiarize myslef with MCC | [15 empty] | Yarentzy | 2022-02-28
Configure System | [15 empty] | Yarentzy | 2022-03-07
Configure I/O pins | [15 empty] | Yarentzy | 2022-03-14
Create a Blinking LED | [15 empty] | Yarentzy | 2022-03-21
Configure UART Serial Communication | [15 empty] | Yarentzy | 2022-03-28
UART Serial Communication and PC Communication | [15 empty] | Yarentzy | 2022-04-10
Design PCB and schematic for circuit | [15 empty] | Grant | 2022-04-18
Order components and parts for power supply | [15 empty] | Grant | 2022-04-08
Develop app to modem communication system | [15 empty] | Martin | 2022-03-20
Configure MCU and ambient temperatrue sensor | [15 empty] | Yarentzy | 2022-04-11
Make connection between app and modem | [15 empty] | Martin | 2022-03-30
Test VAC side of power supply circuit | [15 empty] | Grant | 2022-03-22
Solder and test MCU/control components | [15 empty] | Grant
Validate the modem is able to send and receive the correct data | [15 empty] | Martin | 2022-04-04
Implement Relay to control a large current load | [15 empty] | Yarentzy | 2022-04-18
Establish AC Inputs | [15 empty] | Yarentzy | 2022-04-11
Progress Update Presentations | [15 empty] | All | 2022-03-14
Validate and test full power supply circuit | [15 empty] | Grant | 2022-04-20
Implement GUI over the app | [15 empty] | Martin | 2022-04-12
Validate the whole cellular subsystem is working together | [15 empty] | Martin | 2022-04-11
Accept Input from PC | [15 empty] | Yarentzy | 2022-04-11
Final Presentation | [15 empty] | All | 2022-04-13
Subsystem Presentations | [15 empty] | All | 2022-04-24
Final Report | [15 empty] | All | 2022-04-30