## Sheet1
Item Testing | Success Criteria | Methodology | Status | Responsible Engineer(s)
Battery Output | The battery will output a DC voltage of +12V for a specified run time on the specified loads. | Set up the battery with the inverter and VAC since it is the largest load and test operation. | Tested | Grant Franklin
MCU Input | The +12V DC from the battery will be stepped down to 3.3V for the temperature controlling MCU system. | Create an input voltage and current that mimics the battery and use a multimeter to assure that the output of the Buck converter is 3.3V. | Tested | Grant Franklin
Modem Input | The +12V DC from the battery will be stepped down to 5V for the modem. | Create an input voltage and current that mimics the battery and use a multimeter to assure that the output of the Buck converter is 5V. | Tested | Grant Franklin
Inverter Output | The inverter correctly changes the +12V DC from the battery to 110V AC that will route to the VAC. | Create an input voltage and current that mimics the battery and use a multimeter to assure that the output of the inverter is an AC 110-115V. | Tested | Grant Franklin
Solar Panel Charging | The mounted solar panel will provide sufficient charging for the battery at ~14V. | Use a multimeter to check that power coming from the solar panel and solar charge controller is a DC 14V.​ | Tested | Grant Franklin
12V Outlet Charging | The +12V DC from the car outlet will provide sufficient charging for the battery at ~14V. | Use a multimeter to check that power coming from the 12V car outlet is a DC 14V when the car is on.​ | Untested - 404 | Grant Franklin
Input Power Switching | The control circuit will be able to correctly choose which power source to use. | When the solar panel relay receives a control signal, the connected relay should be outputting 14W to charge the battery. Repeat for the car outlet. | Untested - 404 | Grant Franklin
Solar Panel Circuit Functionality | The circuit will correctly step down the voltage to a value within the specifications of the MCU. If this value is >=13.9V, the output is 3V to the MCU. Otherwise output 0V. | Set up the circuit with inputs higher, lower and at the threshold voltage and record output values with a multimeter. | Untested - 404 | Grant Franklin
App Receiving | App can recieve temp data and battery data via cellular data | Change the displayed in and out temps in the app with a text message | Tested | Martin Rennaker
modem Transmitting | Can send texts from the modem via at commands | use Putty to send at commands to the modem to send a text and verify that it send | Tested | Martin Rennaker
App sending | App can send a desired temp based on user input | enter a temp into the app, press a send button and check that the message was recieved by the target device | Tested | Martin Rennaker
modem Receiving | can recieve and read texts on the modem | send a text to the modem and using putty and at commands read the text | Tested | Martin Rennaker
Notification | The app can send notifications to the phone, the user can toggle on or off different notifications and the app will react and not send or send a notification based on the toggled state | toggle on a battery life notification, send the app a corresponding battery update, check if notification was received. toggle off battery life notification, repeat and verify the notification was not recieved. | Tested | Martin Rennaker
Modem Power | The modem's power consumption will not exceed the 5V at 1 A | modem will be powered using a usb 1A wall plug, so as long as it is operating correctly with this power it is under the power requirement | Tested | Martin Rennaker
correct entry verification | app will only accept temperatures in the send to device box and phone numbers in the add a device box | if an invalid entry is entered into the box the app will not crash it will simply notify the user of the incorrect entry | Tested | Martin Rennaker
out of range temp detection | will double check with the user if the entered desired temp is less than 40 deg F or higher than 90 deg F | if the user enters a temp out of range ask the user to press the button again to verify | Tested | Martin Rennaker
change device verification | if the user tries to add another device while one is connected it will verify with the user | if a device is connected and the user tries to add another device ask the user to press the button again | Tested | Martin Rennaker
device removal | if a device is removed the app should remove all current data and display that a device is not connected | connect a device and send all the information then disconnect the device and verify that the info was removed from the app | Tested | Martin Rennaker
device connection | when adding a device app will attempt to make a handshake with a test message and once a response is recieved will update the connection status on the home page | attepmt to add phone as device and wait for the test text message, then send info to update app and verify that the status is updated and the connection status is updated | Tested | Martin Rennaker
Backgroud data parsing and notifications | The app will update the information while in the background and send notifications based on that data and the noification toggle status | open another app while the app is in the background, and send the phone text updates and verify that the app will still send notifications based off the data sent and the status of the toggle | Tested | Martin Rennaker
Startup Permissions | The app will ask the user permission to send and receive text messages on initial startup | Will uninstall and reinstall the app and verify that it has a SMS permission popup | Tested | Martin Rennaker
VAC Cooling Specifications | The VAC's minimum temperature output is 62 degrees fahrenheit | VAC unit will be placed in a crossover vehicle and data of the maximum cooling capacity capabillity will be collected | Tested | Yarentzy Magallanes
Temperature Sensor | Both temperature sensors report the same measurement | Redundancy will assure accuracy. Two temperature probes will be taking ambient readings. A comparison of these inputs will assure functionality. | Tested | Yarentzy Magallanes
MCU UART Data Receiving | The MCU can receive a setpoint and react to given setpoint | This will test the functionallities of the UART communication between the MCU and a PC. The MCU will recive input from the PC and toggle an LED accordingly | Tested | Yarentzy Magallanes
MCU Data Transmitting | The MCU shall output temperature readings to be received by the application | Temperature will be read using the probes and interpreted into digital signals to them be outputted to the console. | Tested | Yarentzy Magallanes
Measurement Periods | The MCU shall receive and output the temperature to the application every 2 seconds | The temperature sensor data wil be redirected to an output pin which will then be measured by an oscilliscope to determine the frequency of full data transmission | Tested | Yarentzy Magallanes